## Task Tracker
TASK TRACKER
Name: | Gurminder Singh |  |  |  | Date: | 25-11-2020
TASK TITLE | STATUS | PRIORITY | START DATE | DUE DATE | PCT OF TASK COMPLETE | COMMENTS | STATUS MENU | PRIORITY MENU
Discussion for EER diagram | ☐ | HIGH | 19/11/2020 | 24/11/2020 | 100% | Rough EER model diagram designed | ☐ | HIGH
Finalised the EER model diagram after having scrum meeting | ☒ | MEDIUM | 25/11/2020 | 25/11/2020 | 100% | Done with EER model Diagram | ☒ | MEDIUM
discussed queries and divided tasks | ☐ | LOW | 26/11/2020 | 30/11/2020 | 80% | work in progress |  | LOW
collected data and populated database | ☒ | HIGH | 2020-01-11 | 08/12/2020 | 100% | done |  | LOW
started working on 3,4,5, 6 , 7 questions | ☐ | HIGH | 2020-02-11 | 08/12/2020 | 80% | work in progress
done with queries and evaluate results | ☒ | HIGH | 01/12/2020 | 08/12/2020 | 100% | done with queries
started creating technical report | ☒ | HIGH | 06/12/2020 | 08/12/2020 | 100% | done with technical report
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
100%